## Form 2
|  |  | Backfilling Testing Form |  |  |  | Form 2
Reference RFI No: CC-17 |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: Form 2 |  |  | Inspection date: 7/13/2018 |  | Inspection time: 2:15 AM
Unit: Barbeque area |  |  | System: Clean water |  | System: Above Ground Piping Works
Inspected Item Tag |  |  | qwe
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Backfilling completed in correct elevation
2 | Backfilled material has been compacted to required degree
3 | Backfilling material is clean
4 | Backfilling compaction test result is acceptable
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)