## RFI Form
[6 empty] | REQUEST FOR INSPECTION | [10 empty] | RFI Form
[6 empty] | NATALYA CONSTRUCTION | [6 empty] | BROWN'S HOUSE PROJECT
SECTION 1 | RFI NUMBER |  |  | Automaticaly generated by software (SW) | [10 empty] | DATE |  |  | SW
| SUBCONTRACTOR |  |  | SW (from user information)
| DISCIPLINE |  |  | SW (from user information)
| FROM | SW (from user information) | [5 empty] | SIGNATURE
| TO | Filled by User (U) (Dropdown) | [5 empty] | CC |  |  | U (Dropdown)
| ITEMS TO BE INSPECTED |  |  |  | U (Typed)
| INSPECTION DATE / TIME |  |  |  | U (Calendar) |  |  |  |  | UNIT |  |  |  | U (Dropdown)
| REFERENCE ITP NR. |  |  |  | U (Dropdown) |  |  |  |  | ITP PHASE |  |  |  | U (Dropdown)
| FORMS ATTACHED |  |  |  | SW (from ITP Phase information)
| REFERENCE DRAWINGS |  |  |  | U (Dropdown)
| CONTRACTOR INSPECTION POINT | [6 empty] | Hold Point | [6 empty] | Witness Point
| COMPANY INSPECTION POINT | [6 empty] | Hold Point | [6 empty] | Witness Point
| THIRD PARTY INSPECTION POINT | [6 empty] | Hold Point | [6 empty] | Witness Point |  |  |  | N/A
NOTES:
SW (from ITP Phase information)
ACKNOWLEDGEMENT OF RECEIPT
(for RFI by e-mail, copy of mail receipt is sufficient and shall be attached during inspection)
|  |  | OWNER | [6 empty] | THIRD PARTY (if required)
Name
Signature
Date (dd-mmm-yy)
SECTION 2
PRESENCE DURING INSPECTION
| CONTRACTOR |  |  |  | N/A |  | No |  |  |  | Yes |  |  | Signature
(if present)
| OWNER |  |  |  | N/A |  | No |  |  |  | Yes |  |  | Signature
(if present)
| THIRD PARTY |  |  |  | N/A |  | No |  |  |  | Yes |  |  | Signature
(if present)
ASSESSMENT
| INSPECTION RESULTS | [7 empty] | Accepted |  |  | Rejected |  |  |  | Accepted w Punches
REASONS FOR REJECTION (if any)
|  |  | CONTRACTOR |  |  |  | OWNER | [7 empty] | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Punch Form
Reference RFI No: |  |  | PUNCH FORM | [7 empty] | PUNCH FORM
|  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
PROJECT |  | UNIT | SYSTEM | SUBSYSTEM | [5 empty] | DISCIPLINE |  | DATE
BHP
Item Nr. | TCM Nr. (As per MCDB) | TAG | Description |  | Originator | Company of Originator | Responsibility to Solve | Priority | Priority Confirmation (by Comm.) | Closure
[10 empty] | Subcontractor (date & signature) | Contractor (date & signature) | OWNER (date & signature)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Legend for priority |  | A: Major nonconformities B: Item which is not affecting the structure C: Minor nonconformities
ACCEPTANCE |  |  | SUBCONTRACTOR | CONTRACTOR | [5 empty] | OWNER
Name
Signature
Date

## Form 1
|  |  | Excavation Checking Form |  |  |  | Form 1
Reference RFI No: |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: |  |  | Inspection Date: |  | Inspection Time:
Unit: |  |  | System: |  | Subsystem:
Inspected Item Tag
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Excavation done as per approved drawings
2 | Excavation width is as per drawings
3 | Excavation depth is as per drawings
4 | Excavated soil is removed from site
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Form 2
|  |  | Backfilling Testing Form |  |  |  | Form 2
Reference RFI No: CC-3 |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: Form 2 |  |  | Inspection date: 7/14/2018 |  | Inspection time: 5:00 PM
Unit: Barbeque area |  |  | System: Clean water |  | System: Above Ground Piping Works
Inspected Item Tag |  |  | qwe qweqew
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Backfilling completed in correct elevation
2 | Backfilled material has been compacted to required degree
3 | Backfilling material is clean
4 | Backfilling compaction test result is acceptable
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Form 3
|  |  | Rebar & Formwork Checking Form |  |  |  | Form 3
Reference RFI No: |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: |  |  | Inspection Date: |  | Inspection Time:
Unit: |  |  | System: |  | Subsystem:
Inspected Item Tag
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Rebar is placed as per the drawings
2 | Rebar clean, free from dust and rust
3 | Formwork is placed as per drawings
4 | Formwork is supported properly
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Form 4
|  |  | Concreting Check Form |  |  |  | Form 4
Reference RFI No: |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: |  |  | Inspection Date: |  | Inspection Time:
Unit: |  |  | System: |  | Subsystem:
Inspected Item Tag
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Concrete is purchased as per the requirements
2 | Concrete is in correct strength, workability and time
3 | Concrete is placed max 1 m height
4 | Concrete compaction is done as required
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Form 5
|  |  | Material Approval Form |  |  |  | Form 5
Reference RFI No: |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: |  |  | Inspection Date: |  | Inspection Time:
Unit: |  |  | System: |  | Subsystem:
Material to be Approved:
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Material is as per approved drawings
2 | Material quality is acceptable
3 | Material supplyer is acceptable
4 | Material deliveries are acceptable
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Form 6
|  |  | Roof Material application Check Form |  |  |  | Form 6
Reference RFI No: |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: |  |  | Inspection Date: |  | Inspection Time:
Unit: |  |  | System: |  | Subsystem:
Inspected Item Tag
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Roof material bottom is part is applied as per drawings
2 | Roof material bonding agent is applied
3 | Roof material insulation is applied
4 | Roof material finishing is applied
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Form 7
|  |  | Painting Application Check Form |  |  |  | Form 7
Reference RFI No: |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: |  |  | Inspection Date: |  | Inspection Time:
Unit: |  |  | System: |  | Subsystem:
Inspected Item Tag
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Paint material is in approved color
2 | Painting primer is applied correctly
3 | Painting first coat is applied correctly
4 | Painting final coat is applied correctly
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Form 8
|  |  | Tiling Application Check Form |  |  |  | Form 8
Reference RFI No: |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: |  |  | Inspection Date: |  | Inspection Time:
Unit: |  |  | System: |  | Subsystem:
Inspected Item Tag
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Tiling is in approved color
2 | Tiling glue is applied correctly
3 | Tiling is applied correctly
4 | Joint filling is applied correctly
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Form 9
|  |  | Windows and Doors Check Form |  |  |  | Form 9
Reference RFI No: |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: |  |  | Inspection Date: |  | Inspection Time:
Unit: |  |  | System: |  | Subsystem:
Inspected Item Tag
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Windows are placed correctly
2 | Doors are placed correctly
3 | Windows and doors handles are placed correctly
4 | Joint filler is applied correctly
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)

## Form 10
|  |  | Landscaping Check Form |  |  |  | Form 10
Reference RFI No: |  |  | NATALYA CONSTRUCTION |  | BROWN'S HOUSE PROJECT
Form no: |  |  | Inspection Date: |  | Inspection Time:
Unit: |  |  | System: |  | Subsystem:
Inspected Item Tag
# | Inspection Description |  |  |  | Accepted |  |  | Rejected
1 | Landscaping area is ready for grass placement
2 | Planted trees are acceptable
3 | Landscaping grass is placed as per the drawings
4 | Trees are planted as per the drawings
If one of the inspection descripton is "Accepted with Punches" then Punch form should be filled
|  | CONTRACTOR |  | OWNER |  | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)