## RFI Form
[6 empty] | REQUEST FOR INSPECTION | [10 empty] | RFI Form
[6 empty] | NATALYA CONSTRUCTION | [6 empty] | BROWN'S HOUSE PROJECT
SECTION 1 | RFI NUMBER |  |  | CC-4 | [10 empty] | DATE |  |  | 7/13/2018
| SUBCONTRACTOR |  |  | Subcontractor Organization
| DISCIPLINE |  |  | Civil
| FROM | Sub1 Sub1 | [5 empty] | SIGNATURE
| TO | Sub2 Sub2 | [5 empty] | CC |  |  | U (Dropdown)
| ITEMS TO BE INSPECTED |  |  |  | D1
| INSPECTION DATE / TIME |  |  |  | 7/14/2018 |  |  |  |  | UNIT |  |  |  | Barbeque area
| REFERENCE ITP NR. |  |  |  | 4.2 |  |  |  |  | ITP PHASE |  |  |  | Backfilling completion with correct elevation
| FORMS ATTACHED |  |  |  | Form 1
| REFERENCE DRAWINGS |  |  |  | U (Dropdown)
| CONTRACTOR INSPECTION POINT | [5 empty] | X | Hold Point | [6 empty] | Witness Point
| COMPANY INSPECTION POINT | [6 empty] | Hold Point | [6 empty] | Witness Point
| THIRD PARTY INSPECTION POINT | [6 empty] | Hold Point | [6 empty] | Witness Point |  |  |  | N/A
NOTES:
SW (from ITP Phase information)
ACKNOWLEDGEMENT OF RECEIPT
(for RFI by e-mail, copy of mail receipt is sufficient and shall be attached during inspection)
|  |  | OWNER | [6 empty] | THIRD PARTY (if required)
Name
Signature
Date (dd-mmm-yy)
SECTION 2
PRESENCE DURING INSPECTION
| CONTRACTOR |  |  |  | N/A |  | No |  |  |  | Yes |  |  | Signature
(if present)
| OWNER |  |  |  | N/A |  | No |  |  |  | Yes |  |  | Signature
(if present)
| THIRD PARTY |  |  |  | N/A |  | No |  |  |  | Yes |  |  | Signature
(if present)
ASSESSMENT
| INSPECTION RESULTS | [7 empty] | Accepted |  |  | Rejected |  |  |  | Accepted w Punches
REASONS FOR REJECTION (if any)
|  |  | CONTRACTOR |  |  |  | OWNER | [7 empty] | THIRD PARTY
Name
Signature
Date (dd-mmm-yy)